## Schedule
Task | Duration | Depends_On | O | M | P
A | 5
B | 4
C | 7 | A
D | 7 | B
E | 8 | B
F | 5 | B
G | 8 | C, D
I | 2 | F
H | 11 | E, I
J | 12 | F
K | 11 | H, J

## Summary
Project_Duration | Critical_Path
34 | B -> E -> H -> K